## Staffing plan
Epic and Salesforce CRM and patient care program: best-case staffing plan
FTE by phase. Blue values are inputs; edit them and totals recalculate.
# | Group | Role | Pod | Level | Location | Key skills | Discovery and design | Build | Test | Deploy and hypercare | Avg FTE
1 | Leadership and architecture | Program manager leader | All | Senior manager | Onshore | Healthcare program delivery, multi-vendor governance, Epic and Salesforce programs | 1 | 1 | 1 | 1 | 1
2 | Leadership and architecture | Solution architect | All | Manager / senior manager | Onshore | End-to-end solution design, Health Cloud, Epic touchpoints, discovery leadership | 1 | 1 | 0.5 | 0.5 | 0.75
3 | Leadership and architecture | Technical architect (Salesforce) | All | Manager | Onshore | Salesforce platform architecture, Health Cloud data model, sharing, scale | 1 | 1 | 0.5 | 0.5 | 0.75
4 | Leadership and architecture | Integration architect (Epic interoperability) | All | Manager | Onshore | FHIR, HL7 v2, Epic APIs, middleware patterns, event-driven integration | 1 | 1 | 0.5 | 0.25 | 0.6875
5 | Leadership and architecture | Data architect | All | Senior consultant / manager | Onshore | Patient identity matching, data migration strategy, Data Cloud, analytics | 0.5 | 1 | 0.5 | 0.25 | 0.5625
6 | Leadership and architecture | Security architect | All | Senior consultant | Onshore | PHI access model, Shield and encryption, field-level security, audit | 0.5 | 0.25 | 0.25 | 0.25 | 0.3125
7 | Leadership and architecture | Epic application analyst | Billing and revenue | Senior consultant | Onshore | Epic certified: Resolute, Cadence, MyChart | 1 | 1 | 0.5 | 0.5 | 0.75
8 | Functional and design | Business analyst, CRM | CRM | Consultant / senior consultant | Onshore | Requirements, user stories, patient engagement and service processes | 1 | 1 | 0.5 | 0.25 | 0.6875
9 | Functional and design | Business analyst, patient care | Patient care | Consultant / senior consultant | Onshore | Care coordination, care plans, scheduling workflows | 1 | 1 | 0.5 | 0.25 | 0.6875
10 | Functional and design | Business analyst, billing and revenue | Billing and revenue | Senior consultant | Onshore | Revenue cycle, patient estimates, payments, Epic billing touchpoints | 1 | 1 | 0.5 | 0.25 | 0.6875
11 | Functional and design | UX designer | All | Senior consultant | Onshore | Patient and staff experience design, accessibility | 1 | 0.5 | 0 | 0 | 0.375
12 | Delivery pods | Dev lead, CRM | CRM | Senior consultant | Onshore | Salesforce development lead, Health Cloud, Service Cloud | 1 | 1 | 0.5 | 0.5 | 0.75
13 | Delivery pods | Salesforce developer, CRM 1 | CRM | Consultant | Offshore | Apex, LWC, Flow, Health Cloud | 0 | 1 | 0.5 | 0 | 0.375
14 | Delivery pods | Salesforce developer, CRM 2 | CRM | Consultant | Offshore | Apex, LWC, Flow, Experience Cloud | 0 | 1 | 0.5 | 0 | 0.375
15 | Delivery pods | Dev lead, patient care | Patient care | Senior consultant | Onshore | Salesforce development lead, Health Cloud care management | 1 | 1 | 0.5 | 0.5 | 0.75
16 | Delivery pods | Salesforce developer, patient care 1 | Patient care | Consultant | Offshore | Apex, LWC, Flow, Health Cloud | 0 | 1 | 0.5 | 0 | 0.375
17 | Delivery pods | Salesforce developer, patient care 2 | Patient care | Consultant | Offshore | Apex, LWC, Flow, scheduling | 0 | 1 | 0.5 | 0 | 0.375
18 | Delivery pods | Dev lead, billing and revenue | Billing and revenue | Senior consultant | Onshore | Salesforce development lead, integration-heavy, payments | 1 | 1 | 0.5 | 0.5 | 0.75
19 | Delivery pods | Salesforce developer, billing and revenue | Billing and revenue | Consultant | Offshore | Apex, LWC, Flow, payments | 0 | 1 | 0.5 | 0 | 0.375
20 | Delivery pods | Integration developer, billing and revenue | Billing and revenue | Consultant | Offshore | APIs, middleware, FHIR resources (synthetic data) | 0 | 1 | 0.5 | 0 | 0.375
21 | Platform services | Integration developer (FHIR/HL7, middleware) | All | Senior consultant | Onshore | FHIR, HL7 v2, middleware build, Epic interface testing | 0 | 1 | 1 | 0.5 | 0.625
22 | Platform services | Data migration developer | All | Consultant | Onshore | ETL, data loads, reconciliation, identity matching | 0 | 1 | 0.5 | 1 | 0.625
23 | Platform services | DevOps / release engineer | All | Senior consultant | Offshore | CI/CD, source control, environment strategy, release management | 0.25 | 1 | 1 | 1 | 0.8125
24 | Testing | Test lead | All | Senior consultant | Onshore | Test strategy, SIT and UAT management, defect governance | 0.5 | 1 | 1 | 0.5 | 0.75
25 | Testing | Test automation engineer | All | Senior consultant | Offshore | Salesforce test automation, regression suites | 0 | 1 | 1 | 0.25 | 0.5625
26 | Testing | Test data and environment analyst | All | Consultant | Onshore | Synthetic and de-identified data, environment readiness | 0 | 1 | 1 | 0.25 | 0.5625
27 | Testing | Integration tester (Epic to Salesforce) | All | Consultant | Onshore | End-to-end interface testing with PHI-bound data | 0 | 0.5 | 1 | 0.5 | 0.5
28 | Testing | Functional tester 1 | All | Analyst / consultant | Offshore | Functional and regression testing, synthetic data | 0 | 0.5 | 1 | 0.25 | 0.4375
29 | Testing | Functional tester 2 | All | Analyst / consultant | Offshore | Functional and regression testing, synthetic data | 0 | 0.5 | 1 | 0.25 | 0.4375
30 | Change and adoption | OCM and training lead | All | Manager / senior consultant | Onshore | Clinical adoption, training design, communications | 0.5 | 0.25 | 0.5 | 1 | 0.5625
|  | Total FTE |  |  |  |  | 14.25 | 26.5 | 18.75 | 11 | 17.625
|  | Onshore FTE |  |  |  |  | 14 | 17.5 | 11.75 | 9.25 | 13.125
|  | Offshore FTE |  |  |  |  | 0.25 | 9 | 7 | 1.75 | 4.5
|  | Named roles |  |  |  |  | 30

## Pod summary
Build-phase headcount and FTE by pod
Pod | Onshore roles | Offshore roles | Build FTE
CRM | 2 | 2 | 4 | CRM
Patient care | 2 | 2 | 4 | Patient care
Billing and revenue | 3 | 2 | 5 | Billing and revenue
Shared (all pods) | 13 | 4 | 13.5 | All
Total | 20 | 10 | 26.5

## Assumptions
Planning assumptions
Assumption | Source
Phases: discovery and design (~10 weeks), build (~6 sprints), test (SIT and UAT), deploy and hypercare | Planning assumption
Stack finalizes during discovery; Epic plus Salesforce is the working assumption | User
Client restricts PHI from leaving the country; offshore roles work with synthetic or de-identified data | Planning assumption
Onshore required where a role touches production PHI, runs client workshops, or owns Epic integration testing | Planning assumption
Unified testing team: one test lead plus five testers | User
Three delivery pods: CRM, patient care modules, billing and revenue | User
FTE values are planning estimates by phase; Avg FTE is a simple average across the four phases, not duration-weighted | Planning assumption

## Client-provided
Client-provided roles (assumed, not staffed by us)
Role | Notes
Executive sponsor | Decision authority and escalation
Product owner, one per pod | Backlog ownership and acceptance
Clinical informaticist or clinical SME | Clinical workflow validation
Client Epic analysts and Epic integration team | Works alongside the Epic application analyst
Compliance and privacy officer | Sign-off on PHI access model and data handling

## Risks and options
Expected pushback and options
Item | Detail
Plan size | 30 roles is heavy before the stack is chosen. Minimum viable version moves UX, security architect and data architect to fractional shared resources and folds the test data role into the test lead (about 24 roles).
Epic application analyst | Hardest role to fill internally because Epic certification requires organizational sponsorship. Good test case for the matcher's no-strong-match behavior.
Pod sizing | Original plan had 2 onshore leads and 4 offshore developers across 3 pods. This plan uses 3 leads and 6 developers so every pod is led and evenly staffed.
Testing ratio | Testing headcount roughly equals development; automation and test data roles justify the ratio for healthcare regression and UAT.